## Team
Initials | First | Last | Email | GitHub Username
np | Neel | Patel | neel.24patel@gmail.com | Neelmufc
dp | Drashti | Patel | drashti_patel04@yahoo.in | DrashtiSSW
kp | Kajal | Patel | kjp396@gmail.com | Kajal396
ns | Nikhil | sheshagiri | nikhilseshagiri@gmail.com | NikhilNS
|  |  | GitHub Repository: | ssw555tmxx2015s

## Backlog
Sprint | Story ID | Story Name | Acc Tests | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed | Added
1 | US01 | phone number should be of 10 digit | AT01 | np,dp | Done | 50 | 40 | 40 | 20 | 2015-02-26 | 2015-02-21
1 | US02 | Email id should be valid(contain @ and .) | AT02 | kp,ns | Done | 40 | 30 | 32 | 20 | 2015-02-26 | 2015-02-21

## Stories
Story ID | Story Name | Story Description | Acc Tests | Est Size | Est Time
US01 | phone number should be of 10 digit | Make sure that phone nmber should be of 10 digits | AT01 | 50 | 40
US02 | Email id should be valid(contain @ and .) | Make sure that email id should be valid | AT02 | 40 | 30
US03 | 1. Death date before birth date
US04 | 2. Marriage to sibling
US05 | 3. person cannot be married to 2 persons at a time
US06 | 4. children’s birthdate cannot be before father’s
US07 | 5. children’s birthdate cannot be before mother’s
US08 | 6. children’s birthdate cannot be before parents turn 21
US09 | 7. male sex marriage
US10 | 8. female sex marriage
US11 | 9. marriage cannot be done before 21
US12 | 10. children’s last name should be of father’s or mother’s
US13 | 12. marriage to dead person should be prevented
US14 | 13. occupation should be none before 18
US15 | birthdate cannot be after current date
US16 | 16. siblings should have minimum 1 common parent
US17 | 17. siblings should have maximum 2 common parent
US18 | 18. First name and last name should be characters
US19 | 19. Marriage date should not be after death date
US20 | 20. Marriage before birth is not possible
US21 | 21. Phone numbers should not have characters
US22 | 22. Home telephone and work telephone cannot be same
US23 | 23. First name cannot be null
US24 | 24. Date should not be greater than 29 in leap year
US25 | 25. Work and Personal phone should not b same

## Tests
AT ID | Story ID | Story Name | Input | Expected Output | Status
AT01 | US01 | Phone number should be of 10 digit | Phone number is taken as input(1234567890) | No error message | Passed
AT02 | US02 | Email id should be valid | Email id is taken as input(neel.24patel@gmail.com) | No error message | Passed

## Burndown
Date | Remaining Stories | Story Velocity | LOC | Min | Code Velocity
2015-02-19 | 25 | 0 | 0 | 0 | 0
2015-02-26 | 23 | 2 | 75 | 50 | 90

## Sprint1
Story ID | Story Name | Acc Tests | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US01 | phone number should be of 10 digit | AT01 | np,dp | Done | 50 | 40 | 40 | 20 | 2015-02-26
T01.01 | Check nmber of digits |  | np,dp
US02 | Email id should be valid(contain @ and .) | AT02 | kp,ns | Done | 40 | 30 | 32 | 20 | 2015-02-26
T02.01 | Compare with email template |  | kp,ns | Done

## Sprint2
Story ID | Story Name | Acc Tests | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed

## Sprint3
Story ID | Story Name | Acc Tests | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed

## Sprint4
Story ID | Story Name | Acc Tests | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed

## Sprint5
Story ID | Story Name | Acc Tests | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed