## Team
Initials | First | Last | Email | GitHub Username
np | Neel | Patel | neel.24patel@gmail.com | Neelmufc
dp | Drashti | Patel | drashti_patel04@yahoo.in | DrashtiSSW
kp | Kajal | Patel | kjp396@gmail.com | Kajal396
ns | Nikhil | sheshagiri | nikhilseshagiri@gmail.com
|  |  | GitHub Repository: | ssw555tmxx2015s

## Backlog
Sprint | Story ID | Story Name | Acc Tests | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed | Added
1 | US01 | phone number should be of 10 digit | AT01 | np,dp | Done | 50 | 40 | 40 | 20 | 2015-02-26 | 2015-02-21
1 | US02 | Email id should be valid(contain @ and .) | AT02 | kp,ns | Done | 40 | 30 | 30 | 20 | 2015-02-26 | 2015-02-21
2 | US03 | Personal phone and work phone should not be same | AT03 | kp,ns | Done | 30 | 20 | 20 | 20 | 2015-03-11 | 2015-02-21
2 | US04 | Personal phone and residence phone should not be same | AT04 | kp,ns | Done | 30 | 20 | 20 | 10 | 2015-03-11 | 2015-02-21
2 | US05 | Work and residence phone should not be same | AT05 | kp,ns | Done | 30 | 20 | 20 | 10 | 2015-03-11 | 2015-02-21
2 | US06 | Name and surname should have characters only | AT06 | np,dp | Done | 30 | 30 | 20 | 30 | 2015-03-11 | 2015-02-21
2 | US07 | First name should not be null. | AT07 | np,dp | Done | 30 | 30 | 20 | 10 | 2015-03-11 | 2015-02-21

## Stories
Story ID | Story Name | Story Description | Acc Tests | Est Size | Est Time
US01 | phone number should be of 10 digit | Make sure that phone nmber should be of 10 digits | AT01 | 50 | 40
US02 | Email id should be valid(contain @ and .) | Make sure that email id should be valid | AT02 | 40 | 30
US03 | Personal phone and work phone should not be same | personal phone number should be different from work phone. | AT03 | 30 | 20
US04 | Personal phone and residence phone should not be same | personal phone number should be different from residence phone. | AT04 | 30 | 20
US05 | Work and residence phone should not be same | work phone number should be different from residence phone. | AT05 | 30 | 20
US06 | Name and surname should have characters only | there should be only characters in Name and Surname. | AT06 | 30 | 30
US07 | First name should not be null. | Name should have some value. | AT07 | 30 | 30

## Tests
AT ID | Story ID | Story Name | Input | Expected Output | Status
AT01 | US01 | Phone number should be of 10 digit | Phone number is taken as input(1234567890) | No error message | Passed
AT02 | US02 | Email id should be valid | Email id is taken as input(neel.24patel@gmail.com) | No error message | Passed
AT03 | US03 | Personal phone and work phone should not be same | Personal phone and work phone | No error message | Passed
AT04 | US04 | Personal phone and residence phone should not be same | Personal phone and residence phone | No error message | Passed
AT05 | US05 | Work and residence phone should not be same | Work phone and residence phone | No error message | Passed
AT06 | US06 | Name and surname should have characters only | First name and surname | No error message | Passed
AT07 | US07 | First name should not be null. | First name and surname | No error message | Passed

## Burndown
Date | Remaining Stories | Story Velocity | LOC | Min | Code Velocity
2015-02-26 | 23 |  | 0
2015-03-12 | 18 | 5 | 70 | 40 | 105
2015-03-26 | 12 | 6 | 120 | 80 | 37.5
2015-04-02 | 6 | 6 | 200 | 150 | 32
2015-04-16 | 0 | 6 | 400 | 80 | 150

## Sprint1
Story ID | Story Name | Acc Tests | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US01 | phone number should be of 10 digit | AT01 | np,dp | Done | 50 | 40 | 40 | 20 | 2015-02-26
T01.01 | Check nmber of digits |  | np,dp
US02 | Email id should be valid(contain @ and .) | AT02 | kp,ns | Done | 40 | 30 | 32 | 20 | 2015-02-26
T02.01 | Compare with email template |  | kp,ns | Done
US03 | Personal phone and work phone should not be same | AT03 | dp,np | Done | 30 | 20 | 20 | 20 | 2015-03-11
T03.01 | Compare personal phone and work phone
US04 | Personal phone and residence phone should not be same | AT04 | dp,np | Done | 30 | 20 | 20 | 10 | 2015-03-12
T04.01 | Compare work phone and personal phone
US05 | Work and residence phone should not be same | AT05 | dp,np | Done | 30 | 20 | 20 | 10 | 2015-03-11
T05.01 | compare work phone and residence phone
US06 | Name and surname should have characters only | AT06 | dp,np | Done | 30 | 30 | 20 | 30 | 2015-03-11
T06.01 | compare name and surname
US07 | First name should not be null. | AT07 | dp,np | Done | 30 | 30 | 20 | 10 | 2015-03-11
T07.01 | check if the name is null or not.

## Sprint2
Story ID | Story Name | Acc Tests | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US03 | Personal phone and work phone should not be same | AT03 | dp,np | Done | 30 | 20 | 20 | 20 | 2015-03-11
T03.01 | Compare personal phone and work phone
US04 | Personal phone and residence phone should not be same | AT04 | dp,np | Done | 30 | 20 | 20 | 10 | 2015-03-12
T04.01 | Compare work phone and personal phone
US05 | Work and residence phone should not be same | AT05 | dp,np | Done | 30 | 20 | 20 | 10 | 2015-03-11
T05.01 | compare work phone and residence phone
US06 | Name and surname should have characters only | AT06 | dp,np | Done | 30 | 30 | 20 | 30 | 2015-03-11
T06.01 | compare name and surname
US07 | First name should not be null. | AT07 | dp,np | Done | 30 | 30 | 20 | 10 | 2015-03-11
T07.01 | check if the name is null or not.

## Sprint3
Story ID | Story Name | Acc Tests | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed

## Sprint4
Story ID | Story Name | Acc Tests | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed

## Sprint5
Story ID | Story Name | Acc Tests | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed